## Backlog
Sprint Backlog Template
Backlog Item | Story Points | Responsible | Status | Original Estimate | Week1 | Week2 | Sprint Review
User Story #1 | 8
Task |  |  |  | 7 | 5 | 3 | 0
Task |  |  |  | 3 | 1 | 1 | 5
Task |  |  |  | 1 | 0.5 | 0 | 3
Task |  |  |  | 0.5 | 1 | 2 | 3
User Story #2 | 1
Task |  |  |  | 3 | 3 | 0.5 | 0.5
Task |  |  |  | 3 | 5 | 5 | 1
Task |  |  |  | 2 | 2 | 5 | 0
Task |  |  |  | 5 | 5 | 9 | 5
User Story #3 | 5
Task |  |  |  | 8 | 6 | 0 | 0
Task |  |  |  | 3 | 1 | 3 | 3
Task |  |  |  | 1.5 | 1 | 0.5 | 0.5
Task |  |  |  | 2 | 0.5 | 0 | 0
User Story #4 | 8
Task |  |  |  | 9 | 4 | 2 | 2
Task |  |  |  | 6 | 6 | 3 | 3
Task |  |  |  | 6 | 2 | 8 | 8
Task |  |  |  | 0.5 | 0.5 | 0.5 | 0.5
User Story #5 | 3
Task |  |  |  | 2 | 1 | 1 | 1
Task |  |  |  | 6 | 6 | 6 | 0.5
Task |  |  |  | 9 | 9 | 9 | 4
Task |  |  |  | 0.5 | 0.5 | 0.5 | 1
Total |  |  |  | 78 | 60 | 59 | 41
Create a Sprint Backlog in Smartsheet

## David
Task | Week #
Created DB
Created DB connection
Set up project log
Get JCDecaux API key
Set up GitHub Repository
Set up Slack integration
Design DB to store data
Write code to get JCDecaux static data
Set up new EC2 instance with miniconda
Place data insertion function
Add scraper to EC2
Function for dynamic data
Function for static data
Create openweather API
Modify the weather_api function
Station map markers
CSS styling

## Archie
Task | Week #
Modify the weather_api function
Station map markers
Make simple flask example page
ML model for predicting
Final web page
Google map with station markers
Scraper
Bike station information
Weather forecast
Charts

## Nonty
Task | Week #
Design the web page
Create Architecture diagram
Get openweather API
Create web page diagram
Revise Architecture diagram
Revise web page diagram
Create mock up diagram
User geo-location (function aborted)
Future predictions (function aborted)
Create weather widget (not used because Archie already incorporated weather info within station info)